## Sprint Board
Epic | Theme | Story | Task ID | Title | Description | Owner | Estimate | Depends on | Status
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S01 — As an engineer, I want a monorepo with enforced module seams and a green pipeline, so that every later task lands on a working, checked baseline | E01-Th01-S01-T01 | Monorepo scaffold | pnpm workspace with `code/backend` (NestJS `grofast-core`), `code/mobile`, `code/frontend`, shared design-system + types packages, TS strict config. | claude-code | M | — | done
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S01 — As an engineer, I want a monorepo with enforced module seams and a green pipeline, so that every later task lands on a working, checked baseline | E01-Th01-S01-T02 | Module boundary lint + shared contracts | ESLint import-boundary rules per NestJS module, schema-per-module DB conventions, shared zod/DTO contract package consumed by all clients. | claude-code | S | E01-Th01-S01-T01 | not_started
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S01 — As an engineer, I want a monorepo with enforced module seams and a green pipeline, so that every later task lands on a working, checked baseline | E01-Th01-S01-T03 | CI pipeline for PRs | GitHub Actions: lint, typecheck, unit + integration tests against ephemeral Postgres/Redis, coverage gate, ASVS L2 checklist evidence job. | claude-code | M | E01-Th01-S01-T02 | not_started
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S01 — As an engineer, I want a monorepo with enforced module seams and a green pipeline, so that every later task lands on a working, checked baseline | E01-Th01-S01-T04 | Container build, registry & supply-chain scan | Multi-stage images for core/realtime/worker/web, SBOM, dependency + container vulnerability scanning on every build. | claude-code | S | E01-Th01-S01-T03 | not_started
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S01 — As an engineer, I want a monorepo with enforced module seams and a green pipeline, so that every later task lands on a working, checked baseline | E01-Th01-S01-T05 | Deploy pipeline + migration pre-deploy job | Staging auto-deploy, prod deploy behind manual gate, forward-only SQL migrations with advisory locks as a pre-deploy job (Arch §10). | claude-code | M | E01-Th01-S01-T04 | not_started
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S02 — As an eng lead, I want all three environments defined in Terraform on a vendor-portable K8s baseline, so that we can pick the cloud vendor late without redesign | E01-Th01-S02-T01 | Terraform skeleton, workspaces & remote state | **[OPEN: cloud vendor]** Root modules, per-env workspaces, locked remote state, provider abstraction so the vendor choice is one module swap. | claude-code | M | E01-Th01-S01-T01 | not_started
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S02 — As an eng lead, I want all three environments defined in Terraform on a vendor-portable K8s baseline, so that we can pick the cloud vendor late without redesign | E01-Th01-S02-T02 | Network + managed Kubernetes cluster | **[OPEN: cloud vendor]** VPC (public LB / private cluster / isolated data subnets, NAT egress), managed K8s, `general` + `realtime` node pools, HPA baseline. | claude-code | L | E01-Th01-S02-T01 | not_started
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S02 — As an eng lead, I want all three environments defined in Terraform on a vendor-portable K8s baseline, so that we can pick the cloud vendor late without redesign | E01-Th01-S02-T03 | Managed Postgres + PostGIS, replica, PITR | **[OPEN: cloud vendor]** Multi-AZ primary + 1 read replica, PostGIS extension, WAL archiving/daily snapshots (35 d PITR), restore-drill script. | claude-code | M | E01-Th01-S02-T01 | not_started
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S02 — As an eng lead, I want all three environments defined in Terraform on a vendor-portable K8s baseline, so that we can pick the cloud vendor late without redesign | E01-Th01-S02-T04 | Managed Redis (HA pair) | **[OPEN: cloud vendor]** HA Redis for cache, cart hot copy, OTP/rate-limit counters, rider GEO set, pub/sub channels; snapshot policy. | claude-code | S | E01-Th01-S02-T01 | not_started
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S02 — As an eng lead, I want all three environments defined in Terraform on a vendor-portable K8s baseline, so that we can pick the cloud vendor late without redesign | E01-Th01-S02-T05 | Redpanda + Meilisearch StatefulSets | 3-node Redpanda on SSD PVs across 3 AZs with tiered retention; Meilisearch primary + read replica StatefulSet. | claude-code | M | E01-Th01-S02-T02 | not_started
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S02 — As an eng lead, I want all three environments defined in Terraform on a vendor-portable K8s baseline, so that we can pick the cloud vendor late without redesign | E01-Th01-S02-T06 | Object storage, CDN + WAF edge | **[OPEN: cloud vendor]** S3-compatible buckets (images, invoices, proofs, feeds) with lifecycle/versioning; CDN + WAF + edge rate limits (OTP endpoints) + TLS 1.2+ termination. | claude-code | M | E01-Th01-S02-T01 | not_started
E01 — Platform foundation | Th01 — Repository, CI/CD & infrastructure-as-code | S02 — As an eng lead, I want all three environments defined in Terraform on a vendor-portable K8s baseline, so that we can pick the cloud vendor late without redesign | E01-Th01-S02-T07 | Secret management & rotation | **[OPEN: cloud vendor]** Cloud secret manager as source of truth → external-secrets into K8s; gateway keys, webhook HMAC secrets, JWT signing keys with `kid` overlap rotation. | claude-code | M | E01-Th01-S02-T02 | not_started
E01 — Platform foundation | Th02 — Observability baseline | S01 — As an on-call engineer, I want traces, metrics, logs and SLO alerts from day one, so that the order path is debuggable before it carries money | E01-Th02-S01-T01 | OpenTelemetry tracing across all deployables | OTel SDK in core/realtime/workers; 100% sampling on the order path, 10% elsewhere; trace ID carried into the outbox envelope so async legs stitch. | claude-code | M | E01-Th01-S01-T02 | not_started
E01 — Platform foundation | Th02 — Observability baseline | S01 — As an on-call engineer, I want traces, metrics, logs and SLO alerts from day one, so that the order path is debuggable before it carries money | E01-Th02-S01-T02 | Prometheus + Grafana: RED + business metrics | Per-endpoint/module RED metrics plus orders/min, payment success rate, ETA hit rate, OOS-after-order rate, feed freshness, consumer lag, socket count; dashboards mirroring BRS objectives. | claude-code | M | E01-Th01-S02-T02 | not_started
E01 — Platform foundation | Th02 — Observability baseline | S01 — As an on-call engineer, I want traces, metrics, logs and SLO alerts from day one, so that the order path is debuggable before it carries money | E01-Th02-S01-T03 | Structured logging with PII redaction | JSON logs (request/trace ID, actor, module) shipped to Loki; logger-layer redaction of phone/address/instrument patterns; 30 d hot / 13 mo cold. | claude-code | S | E01-Th02-S01-T01 | not_started
E01 — Platform foundation | Th02 — Observability baseline | S01 — As an on-call engineer, I want traces, metrics, logs and SLO alerts from day one, so that the order path is debuggable before it carries money | E01-Th02-S01-T04 | SLO burn-rate alerts + runbooks | Multi-window burn-rate alerts on NFR-1/2/3; hard alerts for payment success < 95%, reconciliation backlog, refund SLA, consumer lag, feed staleness; runbook per alert. | claude-code | M | E01-Th02-S01-T02 | not_started
E01 — Platform foundation | Th03 — Identity, RBAC & audit | S01 — As a customer/rider, I want to log in with my phone and an OTP, so that I never manage a password | E01-Th03-S01-T01 | User entity + OTP issue/verify | `user` table (encrypted phone, HMAC lookup index, consent flags), OTP generation/expiry, constant-time compare, DLT SMS send port with sandbox impl. | claude-code | M | E01-Th01-S01-T02, E01-Th01-S02-T03 | not_started
E01 — Platform foundation | Th03 — Identity, RBAC & audit | S01 — As a customer/rider, I want to log in with my phone and an OTP, so that I never manage a password | E01-Th03-S01-T02 | OTP abuse protection | Per-number (3/min, 10/day) and per-IP Redis counters, backoff/lockout, SMS-pump pattern alerting, edge WAF rules wired to app caps. | claude-code | M | E01-Th03-S01-T01, E01-Th01-S02-T06 | not_started
E01 — Platform foundation | Th03 — Identity, RBAC & audit | S01 — As a customer/rider, I want to log in with my phone and an OTP, so that I never manage a password | E01-Th03-S01-T03 | JWT issue + refresh rotation with reuse detection | RS256 15-min access tokens with `kid` rotation, 30-day rotating refresh tokens hashed at rest, reuse detection revoking the token family. | claude-code | M | E01-Th03-S01-T01, E01-Th01-S02-T07 | not_started
E01 — Platform foundation | Th03 — Identity, RBAC & audit | S01 — As a customer/rider, I want to log in with my phone and an OTP, so that I never manage a password | E01-Th03-S01-T04 | Audience claims + gateway auth guard | Customer/rider/admin audience claims, device-binding claim for riders, server-side verification at the gateway guard; cross-audience calls 401/403 and logged. | claude-code | S | E01-Th03-S01-T03 | not_started
E01 — Platform foundation | Th03 — Identity, RBAC & audit | S02 — As an admin owner, I want role-based access with TOTP, so that staff only see their tools and every denial is on the record | E01-Th03-S02-T01 | Admin/staff auth: email + argon2 + mandatory TOTP | Staff user model, argon2 password hashing, TOTP enrolment/verify, 8-hour sessions. | claude-code | M | E01-Th03-S01-T03 | not_started
E01 — Platform foundation | Th03 — Identity, RBAC & audit | S02 — As an admin owner, I want role-based access with TOTP, so that staff only see their tools and every denial is on the record | E01-Th03-S02-T02 | RBAC role/permission model + guards | Role→permission matrix, NestJS guard layer enforcing per-module permissions server-side, JWT role claims, read-only role mutation block. | claude-code | M | E01-Th03-S02-T01 | not_started
E01 — Platform foundation | Th03 — Identity, RBAC & audit | S02 — As an admin owner, I want role-based access with TOTP, so that staff only see their tools and every denial is on the record | E01-Th03-S02-T03 | Partner user row-scoping | Partner-role tokens scoped to `store_id`; list/detail endpoints filtered at the query layer; enumeration attempts rejected. | claude-code | S | E01-Th03-S02-T02 | not_started
E01 — Platform foundation | Th03 — Identity, RBAC & audit | S02 — As an admin owner, I want role-based access with TOTP, so that staff only see their tools and every denial is on the record | E01-Th03-S02-T04 | Denied-attempt audit logging | Every 403 from the RBAC guard emits an audit event with actor, actor_role, attempted action and entity. | claude-code | S | E01-Th03-S02-T02, E01-Th03-S03-T01 | not_started
E01 — Platform foundation | Th03 — Identity, RBAC & audit | S03 — As a compliance owner, I want an immutable audit log covering every money/stock mutation, so that NFR-10 holds by construction | E01-Th03-S03-T01 | Append-only audit schema + append API | `audit_event` monthly-partitioned table, DB-level UPDATE/DELETE revoke, append API with mandatory actor/reason, 7-year retention + yearly archive to object storage. | claude-code | M | E01-Th01-S02-T03 | not_started
E01 — Platform foundation | Th03 — Identity, RBAC & audit | S03 — As a compliance owner, I want an immutable audit log covering every money/stock mutation, so that NFR-10 holds by construction | E01-Th03-S03-T02 | Audit consumer from `audit.*` topic | Idempotent worker projecting `audit.*` outbox events into `audit_event`; duplicate delivery yields exactly one row. | claude-code | S | E01-Th03-S03-T01, E01-Th04-S01-T03 | not_started
E01 — Platform foundation | Th04 — Event backbone, gateway & runtime | S01 — As the platform, I want a transactional outbox relayed to Redpanda plus a worker/realtime runtime, so that domain events are never lost and never double-applied | E01-Th04-S01-T01 | Outbox table + in-transaction write helper | Month-partitioned `outbox` table, partial index `WHERE published_at IS NULL`, transactional helper every module uses to emit events inside its own commit. | claude-code | M | E01-Th01-S02-T03 | not_started
E01 — Platform foundation | Th04 — Event backbone, gateway & runtime | S01 — As the platform, I want a transactional outbox relayed to Redpanda plus a worker/realtime runtime, so that domain events are never lost and never double-applied | E01-Th04-S01-T02 | Outbox relay worker (at-least-once) | Poller/relay publishing unpublished rows to Redpanda, crash-safe with `published_at` marking; survives kill between commit and publish. | claude-code | M | E01-Th04-S01-T01, E01-Th01-S02-T05 | not_started
E01 — Platform foundation | Th04 — Event backbone, gateway & runtime | S01 — As the platform, I want a transactional outbox relayed to Redpanda plus a worker/realtime runtime, so that domain events are never lost and never double-applied | E01-Th04-S01-T03 | Topics, versioned envelope & consumer framework | Topic provisioning (`order.*`, `payment.*`, `stock.*`, `rider.*`, `feed.*`, `audit.*`), versioned envelope with trace ID, worker-pool entrypoint, processed-event key store for idempotency, replay-safety flag for side-effecting consumers. | claude-code | L | E01-Th04-S01-T02 | not_started
E01 — Platform foundation | Th04 — Event backbone, gateway & runtime | S01 — As the platform, I want a transactional outbox relayed to Redpanda plus a worker/realtime runtime, so that domain events are never lost and never double-applied | E01-Th04-S01-T04 | API gateway / BFF ingress | Single ingress: TLS, JWT validation, routing to core vs realtime, per-client request shaping, `Idempotency-Key` enforcement on money-path writes, signed payment-webhook ingress route. | claude-code | M | E01-Th03-S01-T04 | not_started
E01 — Platform foundation | Th04 — Event backbone, gateway & runtime | S01 — As the platform, I want a transactional outbox relayed to Redpanda plus a worker/realtime runtime, so that domain events are never lost and never double-applied | E01-Th04-S01-T05 | Realtime gateway skeleton | Stateless WebSocket deployable: auth handshake against JWT audience, connection registry, Redis pub/sub wiring, health/socket-count metrics for HPA. | claude-code | M | E01-Th04-S01-T04, E01-Th01-S02-T04 | not_started
E02 — Catalog & discovery | Th01 — Serviceability & ETA (PostGIS) | S01 — As a customer, I want to know instantly whether my location is serviceable and which store serves me, so that I never build a dead cart | E02-Th01-S01-T01 | Zone & store schema with GIST + polygon validation | `zone` (PostGIS polygon, eta_params, active), `store` (dark/partner, geo point), `store_zone` mapping; GIST index; self-intersecting/unclosed-ring rejection at save. | claude-code | M | E01-Th01-S02-T03 | not_started
E02 — Catalog & discovery | Th01 — Serviceability & ETA (PostGIS) | S01 — As a customer, I want to know instantly whether my location is serviceable and which store serves me, so that I never build a dead cart | E02-Th01-S01-T02 | Serviceability resolver (`ST_Contains`) with pinned boundary semantics | Location → zone → serving store resolution; documented boundary/vertex and overlapping-zone tiebreak semantics; Redis-cached per session. | claude-code | M | E02-Th01-S01-T01, E01-Th01-S02-T04 | not_started
E02 — Catalog & discovery | Th01 — Serviceability & ETA (PostGIS) | S01 — As a customer, I want to know instantly whether my location is serviceable and which store serves me, so that I never build a dead cart | E02-Th01-S01-T03 | Address book + geocode + zone resolution | `address` CRUD with label/floor/landmark, geocoding port (maps provider [OPEN]), zone_id resolution on save, manual-entry fallback when GPS is denied. | claude-code | M | E02-Th01-S01-T02, E01-Th03-S01-T01 | not_started
E02 — Catalog & discovery | Th01 — Serviceability & ETA (PostGIS) | S01 — As a customer, I want to know instantly whether my location is serviceable and which store serves me, so that I never build a dead cart | E02-Th01-S01-T04 | Not-serviceable state + notify-me capture | API returning the not-serviceable state for points outside all zones, notify-me capture (phone + location), cart creation blocked for unserviceable sessions. | claude-code | S | E02-Th01-S01-T02 | not_started
E02 — Catalog & discovery | Th01 — Serviceability & ETA (PostGIS) | S01 — As a customer, I want to know instantly whether my location is serviceable and which store serves me, so that I never build a dead cart | E02-Th01-S01-T05 | Dynamic ETA computation + zone publish invalidation | ETA from store load + rider availability (Redis), widening/throttle rules when riders are scarce, promise returned at checkout for storage on the order; zone publish invalidates caches ≤ 60 s. | claude-code | M | E02-Th01-S01-T02 | not_started
E02 — Catalog & discovery | Th02 — Catalog | S01 — As a catalog manager, I want SKU/category CRUD with bulk upload, and as a customer I want honest per-store browse and detail, so that the storefront is never wrong | E02-Th02-S01-T01 | SKU & category schema | `sku` (brand, category, pack_size, mrp, images, attributes JSONB + GIN, barcode) and category tree; restricted-category flag field (BR-9). | claude-code | M | E01-Th01-S02-T03 | not_started
E02 — Catalog & discovery | Th02 — Catalog | S01 — As a catalog manager, I want SKU/category CRUD with bulk upload, and as a customer I want honest per-store browse and detail, so that the storefront is never wrong | E02-Th02-S01-T02 | Catalog CRUD API + bulk CSV + BR-9 guard | SKU/category/image CRUD emitting `stock.*`/catalog change events; row-wise bulk CSV with success/reject report; restricted-category publish block on both paths. | claude-code | L | E02-Th02-S01-T01, E01-Th04-S01-T01 | not_started
E02 — Catalog & discovery | Th02 — Catalog | S01 — As a catalog manager, I want SKU/category CRUD with bulk upload, and as a customer I want honest per-store browse and detail, so that the storefront is never wrong | E02-Th02-S01-T03 | Per-store browse API + Redis catalog cache | Category listing filtered to in-stock priced items of the serving store, Redis cache with event-driven invalidation, p95-instrumented; no ghost inventory. | claude-code | M | E02-Th02-S01-T01, E02-Th01-S01-T02 | not_started
E02 — Catalog & discovery | Th02 — Catalog | S01 — As a catalog manager, I want SKU/category CRUD with bulk upload, and as a customer I want honest per-store browse and detail, so that the storefront is never wrong | E02-Th02-S01-T04 | Product detail API | PDP payload: price/MRP/discount, pack size, images, per-store availability; unavailable-at-your-store state for deep links into a non-serving store's SKU. | claude-code | S | E02-Th02-S01-T03 | not_started
E02 — Catalog & discovery | Th03 — Search (Meilisearch) | S01 — As a customer, I want forgiving sub-300 ms search, so that misspellings still find my item | E02-Th03-S01-T01 | Meilisearch index schema & ranking rules | Index of catalog × per-store availability, synonyms, typo tolerance settings, ranking rules tuned for grocery brand/pack queries. | claude-code | M | E01-Th01-S02-T05, E02-Th02-S01-T01 | not_started
E02 — Catalog & discovery | Th03 — Search (Meilisearch) | S01 — As a customer, I want forgiving sub-300 ms search, so that misspellings still find my item | E02-Th03-S01-T02 | Search indexer worker | Redpanda consumer applying catalog and stock events to Meili ≤ 60 s; idempotent; full-reindex command for replay/rebuild. | claude-code | M | E02-Th03-S01-T01, E01-Th04-S01-T03 | not_started
E02 — Catalog & discovery | Th03 — Search (Meilisearch) | S01 — As a customer, I want forgiving sub-300 ms search, so that misspellings still find my item | E02-Th03-S01-T03 | Search API with empty-state alternates | Store-scoped query API, typo-tolerant, < 300 ms budget, alternate suggestions on zero results, graceful degradation if Meili is down (browse unaffected). | claude-code | M | E02-Th03-S01-T01 | not_started
E02 — Catalog & discovery | Th04 — Cart | S01 — As a customer, I want a persistent single-store cart that refuses impossible quantities, so that my cart is always orderable | E02-Th04-S01-T01 | Cart API with Redis hot copy + PG durability | `cart` entity with line snapshots, add/step/remove endpoints, running total, cross-device read-through, restart survival. | claude-code | M | E02-Th02-S01-T03, E01-Th01-S02-T04 | not_started
E02 — Catalog & discovery | Th04 — Cart | S01 — As a customer, I want a persistent single-store cart that refuses impossible quantities, so that my cart is always orderable | E02-Th04-S01-T02 | Single-store rule enforcement (BR-1) | Server-side rejection of mixed-store cart writes; clear/switch prompt contract when the serving store changes. | claude-code | S | E02-Th04-S01-T01, E02-Th01-S01-T02 | not_started
E02 — Catalog & discovery | Th04 — Cart | S01 — As a customer, I want a persistent single-store cart that refuses impossible quantities, so that my cart is always orderable | E02-Th04-S01-T03 | Quantity caps: stock + per-order | Increment guard against `available_qty` and `max_per_order` with per-reason error codes; cart can never exceed either limit. | claude-code | S | E02-Th04-S01-T01 | not_started
E02 — Catalog & discovery | Th05 — Pricing, coupons & invoicing | S01 — As a customer, I want an itemized, tamper-proof bill with working coupons and a GST invoice, so that pricing is transparent and legal | E02-Th05-S01-T01 | Fee & bill computation engine (server-authoritative) | Delivery + small-cart fee rules, GST-inclusive line math, itemized bill DTO; server recomputes on every checkout call; tampered client values rejected and logged. | claude-code | M | E02-Th04-S01-T01 | not_started
E02 — Catalog & discovery | Th05 — Pricing, coupons & invoicing | S01 — As a customer, I want an itemized, tamper-proof bill with working coupons and a GST invoice, so that pricing is transparent and legal | E02-Th05-S01-T02 | Coupon engine (flat/percent, limits, reasons) | `coupon` entity, eligibility (min_cart, store, validity), per-user usage limits + redemption counter, max_discount cap, typed failure reasons. | claude-code | M | E02-Th05-S01-T01 | not_started
E02 — Catalog & discovery | Th05 — Pricing, coupons & invoicing | S01 — As a customer, I want an itemized, tamper-proof bill with working coupons and a GST invoice, so that pricing is transparent and legal | E02-Th05-S01-T03 | GST invoice generation at delivery | Invoice PDF (GSTIN, per-line GST breakup, GST-inclusive prices) rendered on DELIVERED, stored in object storage, linked on the order, 8-year retention. | claude-code | M | E02-Th05-S01-T01, E01-Th01-S02-T06 | not_started
E03 — Ordering & payments | Th01 — Orders: state machine, checkout & reservation | S01 — As a customer, I want my order accepted only if the stock is really there and the charge is really made, so that I'm never disappointed or double-charged | E03-Th01-S01-T01 | Order schema + state machine + transition ledger | `order`/`order_item` tables, states PLACED→PICKING→PACKED→DISPATCHED→DELIVERED/CANCELLED, every transition recorded with actor + timestamp; per-state partial indexes. | claude-code | L | E01-Th01-S02-T03, E01-Th04-S01-T01 | not_started
E03 — Ordering & payments | Th01 — Orders: state machine, checkout & reservation | S01 — As a customer, I want my order accepted only if the stock is really there and the charge is really made, so that I'm never disappointed or double-charged | E03-Th01-S01-T02 | Checkout session API (revalidate + ETA promise) | `POST /v1/checkout`: pricing revalidation, coupon check, ETA computation, inventory soft-check; returns bill + payable + checkout-session ID; stores the promise for placement. | claude-code | M | E03-Th01-S01-T01, E02-Th05-S01-T01, E02-Th01-S01-T05 | not_started
E03 — Ordering & payments | Th01 — Orders: state machine, checkout & reservation | S01 — As a customer, I want my order accepted only if the stock is really there and the charge is really made, so that I'm never disappointed or double-charged | E03-Th01-S01-T03 | Atomic stock reservation transaction | `SELECT … FOR UPDATE` on all `store_inventory` lines → available−/reserved+, insert order + items + payment + outbox rows, single commit; shortfall → full rollback with typed reason. | claude-code | L | E03-Th01-S01-T02, E05-Th01-S01-T01 | not_started
E03 — Ordering & payments | Th01 — Orders: state machine, checkout & reservation | S01 — As a customer, I want my order accepted only if the stock is really there and the charge is really made, so that I'm never disappointed or double-charged | E03-Th01-S01-T04 | Checkout-confirm idempotency | Idempotency on checkout-session ID at API + gateway layer: concurrent and repeat confirms return the same order ID; one order, one reservation, one charge. | claude-code | M | E03-Th01-S01-T03, E01-Th04-S01-T04 | not_started
E03 — Ordering & payments | Th01 — Orders: state machine, checkout & reservation | S01 — As a customer, I want my order accepted only if the stock is really there and the charge is really made, so that I'm never disappointed or double-charged | E03-Th01-S01-T05 | 15-minute unpaid-hold expiry (BR-3) | Hold timer + sweep releasing reservations for payments still PENDING at 15 min, marking payment expired per gateway truth and notifying the customer to retry. | claude-code | M | E03-Th01-S01-T03, E03-Th03-S01-T06 | not_started
E03 — Ordering & payments | Th01 — Orders: state machine, checkout & reservation | S02 — As a customer, I want to cancel, reorder and rate, so that mistakes are cheap and repeat shopping is instant | E03-Th01-S02-T01 | Cancellation + stock release + refund trigger | Pre-dispatch cancel endpoint releasing `reserved_qty` and creating the refund row; post-dispatch cancel refused with reason on both app and API paths. | claude-code | M | E03-Th01-S01-T03, E03-Th03-S01-T07 | not_started
E03 — Ordering & payments | Th01 — Orders: state machine, checkout & reservation | S02 — As a customer, I want to cancel, reorder and rate, so that mistakes are cheap and repeat shopping is instant | E03-Th01-S02-T02 | Order history + one-tap reorder | Paginated history with invoice links; reorder resolves each SKU against current store availability/price, flags unavailable lines, blocks empty-cart checkout. | claude-code | M | E03-Th01-S01-T01, E02-Th04-S01-T01 | not_started
E03 — Ordering & payments | Th01 — Orders: state machine, checkout & reservation | S02 — As a customer, I want to cancel, reorder and rate, so that mistakes are cheap and repeat shopping is instant | E03-Th01-S02-T03 | Ratings + low-rating exception routing | Rating API restricted to DELIVERED orders, reason picker payload at ≤ 3 stars, record routed to the ops exception queue; feature-flagged as non-critical (fails open). | claude-code | S | E03-Th01-S01-T01 | not_started
E03 — Ordering & payments | Th02 — Order events (outbox emission & consumers) | S01 — As a downstream system, I want every order/stock/payment state change as a durable event, so that notifications, picking, analytics and audit are decoupled from checkout | E03-Th02-S01-T01 | Domain event emission for order/stock/payment | Event schemas + in-transaction emission on every order state change, reservation, capture and refund, with actor/reason mandatory for audit. | claude-code | M | E03-Th01-S01-T03, E01-Th04-S01-T01 | not_started
E03 — Ordering & payments | Th02 — Order events (outbox emission & consumers) | S01 — As a downstream system, I want every order/stock/payment state change as a durable event, so that notifications, picking, analytics and audit are decoupled from checkout | E03-Th02-S01-T02 | Consumer idempotency + replay safety verification | Processed-event keys on all consumers, replay mode suppressing side-effecting consumers, projection-rebuild command validated against Postgres truth. | claude-code | M | E03-Th02-S01-T01, E01-Th04-S01-T03 | not_started
E03 — Ordering & payments | Th03 — Payments adapter, webhooks, reconciliation & refunds | S01 — As finance, I want money to be impossible to lose or duplicate, so that BR-4 and objective #4 hold even when the gateway misbehaves | E03-Th03-S01-T01 | Gateway-agnostic payments port + fake gateway | Adapter port (create intent, verify, capture, refund, status), `payment`/`refund` schema with unique `gateway_payment_ref`, in-repo fake gateway implementing the port so all tests run while the vendor is [OPEN]. | claude-code | L | E01-Th01-S01-T02, E01-Th01-S02-T03 | not_started
E03 — Ordering & payments | Th03 — Payments adapter, webhooks, reconciliation & refunds | S01 — As finance, I want money to be impossible to lose or duplicate, so that BR-4 and objective #4 hold even when the gateway misbehaves | E03-Th03-S01-T02 | Intent creation with idempotency key | Create gateway order/intent keyed on checkout-session ID; UPI/card/wallet method selection; no raw instrument data ever received (SAQ-A, gateway-hosted fields/SDK). | claude-code | M | E03-Th03-S01-T01, E03-Th01-S01-T02 | not_started
E03 — Ordering & payments | Th03 — Payments adapter, webhooks, reconciliation & refunds | S01 — As finance, I want money to be impossible to lose or duplicate, so that BR-4 and objective #4 hold even when the gateway misbehaves | E03-Th03-S01-T03 | Server-side capture verification | Client callback triggers a server verify call against the gateway; amount verified server-side; capture confirmed only from gateway truth; result idempotent with the webhook path. | claude-code | M | E03-Th03-S01-T02 | not_started
E03 — Ordering & payments | Th03 — Payments adapter, webhooks, reconciliation & refunds | S01 — As finance, I want money to be impossible to lose or duplicate, so that BR-4 and objective #4 hold even when the gateway misbehaves | E03-Th03-S01-T04 | Signed webhook ingress (HMAC + replay window) | Webhook endpoint behind the gateway: HMAC verification, timestamp window, raw payload persistence, unsigned/wrong-signature/out-of-window rejected with forgery alerting. | claude-code | M | E03-Th03-S01-T01, E01-Th04-S01-T04, E01-Th01-S02-T07 | not_started
E03 — Ordering & payments | Th03 — Payments adapter, webhooks, reconciliation & refunds | S01 — As finance, I want money to be impossible to lose or duplicate, so that BR-4 and objective #4 hold even when the gateway misbehaves | E03-Th03-S01-T05 | Idempotent webhook upsert + state comparison | Upsert keyed `gateway_payment_ref`+type, timestamp precedence for out-of-order events, three-way state comparison (captured+order / captured+no-order → auto-refund / failed+reservation → release). | claude-code | L | E03-Th03-S01-T04, E03-Th01-S01-T03 | not_started
E03 — Ordering & payments | Th03 — Payments adapter, webhooks, reconciliation & refunds | S01 — As finance, I want money to be impossible to lose or duplicate, so that BR-4 and objective #4 hold even when the gateway misbehaves | E03-Th03-S01-T06 | Reconciliation sweep worker (5 min) | Worker querying the gateway status API for payments PENDING > 15 min, resolving per state comparison, covering webhook loss; no phantom orders. | claude-code | M | E03-Th03-S01-T05, E01-Th04-S01-T03 | not_started
E03 — Ordering & payments | Th03 — Payments adapter, webhooks, reconciliation & refunds | S01 — As finance, I want money to be impossible to lose or duplicate, so that BR-4 and objective #4 hold even when the gateway misbehaves | E03-Th03-S01-T07 | Refunds + BR-4 SLA monitor + approval threshold | Refund creation with `sla_deadline` +24 h, gateway call idempotent on refund ID, auto-initiate ≤ ₹2,000 / finance approval > ₹2,000, monitor alerting at ≥ 20 h uninitiated, refund webhooks closing the loop. | claude-code | L | E03-Th03-S01-T05 | not_started
E03 — Ordering & payments | Th04 — Cash on delivery (confirmed for v1, BR-5) | S01 — As a customer, I want COD as a fallback, so that I can order without digital payment — within the caps finance set | E03-Th04-S01-T01 | COD eligibility: BR-5 cap config + risk flag | Ops-configurable per-order cap (default ₹1,500), risky-first-time-user flag, eligibility evaluated at checkout and re-enforced at placement; API rejects ineligible COD regardless of client. | claude-code | M | E03-Th01-S01-T02 | not_started
E03 — Ordering & payments | Th04 — Cash on delivery (confirmed for v1, BR-5) | S01 — As a customer, I want COD as a fallback, so that I can order without digital payment — within the caps finance set | E03-Th04-S01-T02 | COD order placement path | Placement skipping intent/capture, reserving stock at placement, payment row `method=cod` in COD-pending state, BR-3 unpaid-hold logic bypassed; COD-only degraded mode flag for gateway outages. | claude-code | M | E03-Th04-S01-T01, E03-Th01-S01-T03 | not_started
E03 — Ordering & payments | Th04 — Cash on delivery (confirmed for v1, BR-5) | S01 — As a customer, I want COD as a fallback, so that I can order without digital payment — within the caps finance set | E03-Th04-S01-T03 | COD collection, rider float & reconciliation report | Collect-amount exposure to the rider assignment, collection confirmation gate on completion, `cod_float` accounting, daily COD reconciliation report with audit rows per collection. | claude-code | M | E03-Th04-S01-T02, E04-Th03-S01-T02 | not_started
E04 — Fulfillment & logistics | Th01 — Picker workflow | S01 — As a picker, I want a layout-ordered, barcode-verified pick list with an OOS escape hatch, so that I pack fast and honestly | E04-Th01-S01-T01 | Picker-queue projection from `order.placed` | Idempotent consumer building the per-store picker queue sorted by `eta_promised_at`; exactly one entry under duplicate delivery. | claude-code | M | E03-Th02-S01-T01, E01-Th04-S01-T03 | not_started
E04 — Fulfillment & logistics | Th01 — Picker workflow | S01 — As a picker, I want a layout-ordered, barcode-verified pick list with an OOS escape hatch, so that I pack fast and honestly | E04-Th01-S01-T02 | Pick list in store-layout order + accept transition | Store layout positions on `store_inventory`, accept → PICKING transition with actor, list sorted by aisle/bin. | claude-code | M | E04-Th01-S01-T01, E03-Th01-S01-T01 | not_started
E04 — Fulfillment & logistics | Th01 — Picker workflow | S01 — As a picker, I want a layout-ordered, barcode-verified pick list with an OOS escape hatch, so that I pack fast and honestly | E04-Th01-S01-T03 | Barcode verification + pack completion | Per-line scan confirmation matched against SKU barcode, mismatch feedback, pack-complete gate on all lines resolved, PACKED transition with timestamps → `order.packed`. | claude-code | M | E04-Th01-S01-T02 | not_started
E04 — Fulfillment & logistics | Th01 — Picker workflow | S01 — As a picker, I want a layout-ordered, barcode-verified pick list with an OOS escape hatch, so that I pack fast and honestly | E04-Th01-S01-T04 | OOS flag → substitute-or-refund (60 s) | Picker OOS flag, substitute offer to the customer with 60 s timer, accept → line swap + bill delta, reject/timeout → line refund (BR-4 path); order continues partial. | claude-code | L | E04-Th01-S01-T03, E03-Th03-S01-T07, E04-Th05-S01-T02 | not_started
E04 — Fulfillment & logistics | Th02 — Dispatch & rider assignment | S01 — As a rider, I want nearby jobs offered to me automatically, so that I earn without hunting | E04-Th02-S01-T01 | Rider & assignment schema + Redis GEO membership | `rider` (kyc, vehicle, online_status, active_assignment, cod_float) and `assignment` tables; GEO set membership driven by online/offline and active-order state. | claude-code | M | E01-Th01-S02-T03, E01-Th01-S02-T04 | not_started
E04 — Fulfillment & logistics | Th02 — Dispatch & rider assignment | S01 — As a rider, I want nearby jobs offered to me automatically, so that I earn without hunting | E04-Th02-S01-T02 | Offer engine: GEOSEARCH + 30 s TTL | Dispatch worker on `order.packed`: nearest-eligible search, `assignment` OFFERED with TTL, offer pushed via the realtime gateway; accept → ACCEPTED, others never offered. | claude-code | L | E04-Th02-S01-T01, E04-Th04-S01-T01, E01-Th04-S01-T03 | not_started
E04 — Fulfillment & logistics | Th02 — Dispatch & rider assignment | S01 — As a rider, I want nearby jobs offered to me automatically, so that I earn without hunting | E04-Th02-S01-T03 | Decline/timeout cascade + exhaustion → exception queue | Idempotent TTL expiry (survives worker restart, never two concurrent active offers), cascade to next-nearest, exhaustion routes the order to the ops exception queue. | claude-code | M | E04-Th02-S01-T02 | not_started
E04 — Fulfillment & logistics | Th02 — Dispatch & rider assignment | S01 — As a rider, I want nearby jobs offered to me automatically, so that I earn without hunting | E04-Th02-S01-T04 | BR-7 single-active guard + ops force-assign | Riders with an ACCEPTED assignment excluded from candidates; ops force-assign endpoint overriding the cascade with audit. | claude-code | M | E04-Th02-S01-T03 | not_started
E04 — Fulfillment & logistics | Th03 — Rider pickup, delivery & earnings | S01 — As a rider, I want clear verified pickup/drop steps and honest earnings, so that deliveries are error-free and my shift is mine | E04-Th03-S01-T01 | Pickup verification (OTP / scan) | Store-side pickup verification endpoint, `pickup_verified_at` on assignment, DISPATCHED transition gated on it, tracking activation trigger. | claude-code | M | E04-Th02-S01-T02, E03-Th01-S01-T01 | not_started
E04 — Fulfillment & logistics | Th03 — Rider pickup, delivery & earnings | S01 — As a rider, I want clear verified pickup/drop steps and honest earnings, so that deliveries are error-free and my shift is mine | E04-Th03-S01-T02 | Delivery proof (OTP or photo) → object storage | Proof capture and upload, `proof_ref` on assignment, DELIVERED gated on proof at the service layer (raw API attempts blocked), invoice generation trigger. | claude-code | M | E04-Th03-S01-T01, E01-Th01-S02-T06, E02-Th05-S01-T03 | not_started
E04 — Fulfillment & logistics | Th03 — Rider pickup, delivery & earnings | S01 — As a rider, I want clear verified pickup/drop steps and honest earnings, so that deliveries are error-free and my shift is mine | E04-Th03-S01-T03 | Online/offline toggle + earnings ledger | Toggle endpoint propagating to GEO eligibility ≤ 5 s; earnings read model computing per-order payout and daily totals from assignment records. | claude-code | M | E04-Th02-S01-T01, E04-Th03-S01-T02 | not_started
E04 — Fulfillment & logistics | Th04 — Realtime gateway & live tracking | S01 — As a customer, I want the rider on a live map, so that I know when to be at the door | E04-Th04-S01-T01 | GPS ingest → Redis GEO + pub/sub publish | Rider GPS frames over WS (4 s cadence, batched), GEO set write for dispatch, publish to `track:{order_id}`; back-pressure and bad-frame handling. | claude-code | M | E01-Th04-S01-T05, E04-Th02-S01-T01 | not_started
E04 — Fulfillment & logistics | Th04 — Realtime gateway & live tracking | S01 — As a customer, I want the rider on a live map, so that I know when to be at the door | E04-Th04-S01-T02 | Tracking fan-out + order-status bridge | Customer/ops subscriptions per order, `order.*` events bridged onto the same channel so status + position share one socket; per-pod channel subscription management. | claude-code | M | E04-Th04-S01-T01, E03-Th02-S01-T01 | not_started
E04 — Fulfillment & logistics | Th04 — Realtime gateway & live tracking | S01 — As a customer, I want the rider on a live map, so that I know when to be at the door | E04-Th04-S01-T03 | Reconnect resume + state fetch on subscribe | Resubscribe delivers current status and last-known position so a gap never leaves a stale screen; pod-kill reconnect ≤ 10 s. | claude-code | M | E04-Th04-S01-T02 | not_started
E04 — Fulfillment & logistics | Th04 — Realtime gateway & live tracking | S01 — As a customer, I want the rider on a live map, so that I know when to be at the door | E04-Th04-S01-T04 | Polling fallback + rider_location archive | `GET /v1/orders/{id}/track` served from Redis last-known for WS loss; downsampler (1/30 s) writing the day-partitioned `rider_location` archive → warehouse. | claude-code | M | E04-Th04-S01-T01 | not_started
E04 — Fulfillment & logistics | Th05 — Notifications engine | S01 — As the platform, I want a templated push/SMS notification on every lifecycle event, so that customers and riders are never in the dark | E04-Th05-S01-T01 | Template registry + event→template mapping | `notification` schema, DLT template registry (IDs configurable — SMS/DLT provider [OPEN]), lifecycle-event → template mapping table, variable rendering with boundary-length validation. | claude-code | M | E01-Th04-S01-T03 | not_started
E04 — Fulfillment & logistics | Th05 — Notifications engine | S01 — As the platform, I want a templated push/SMS notification on every lifecycle event, so that customers and riders are never in the dark | E04-Th05-S01-T02 | Push sender (FCM/APNs) ≤ 10 s | Notification consumer dispatching push within 10 s of commit, idempotent per event key, device-token management for customer + rider apps. | claude-code | M | E04-Th05-S01-T01 | not_started
E04 — Fulfillment & logistics | Th05 — Notifications engine | S01 — As the platform, I want a templated push/SMS notification on every lifecycle event, so that customers and riders are never in the dark | E04-Th05-S01-T03 | SMS fallback + retry/backoff + ops alert | Push-failure → SMS fallback row within 10 s; double failure retries with backoff and raises an ops alert; no silent loss. | claude-code | M | E04-Th05-S01-T02 | not_started
E05 — Inventory & partners | Th01 — Dark-store inventory | S01 — As an ops manager, I want GRN, adjustments and cycle counts with a full audit trail and alerts, so that system stock matches shelf stock | E05-Th01-S01-T01 | `store_inventory` schema + indexes | PK (store_id, sku_id), price, available/reserved qty, max_per_order, low_stock_threshold, source (grn/feed), layout position; partial low-stock index. | claude-code | M | E02-Th02-S01-T01, E02-Th01-S01-T01 | not_started
E05 — Inventory & partners | Th01 — Dark-store inventory | S01 — As an ops manager, I want GRN, adjustments and cycle counts with a full audit trail and alerts, so that system stock matches shelf stock | E05-Th01-S01-T02 | GRN (goods receipt) | Manual GRN receiving increasing `available_qty`, with actor + reference, emitting `stock.*` + `audit.*` events in-transaction. | claude-code | M | E05-Th01-S01-T01, E01-Th04-S01-T01 | not_started
E05 — Inventory & partners | Th01 — Dark-store inventory | S01 — As an ops manager, I want GRN, adjustments and cycle counts with a full audit trail and alerts, so that system stock matches shelf stock | E05-Th01-S01-T03 | Adjustments & cycle counts with mandatory reason | Adjustment/cycle-count APIs requiring reason + actor, negative-stock guard, all mutations routed exclusively through the inventory module. | claude-code | M | E05-Th01-S01-T02 | not_started
E05 — Inventory & partners | Th01 — Dark-store inventory | S01 — As an ops manager, I want GRN, adjustments and cycle counts with a full audit trail and alerts, so that system stock matches shelf stock | E05-Th01-S01-T04 | Low-stock alerting | Threshold-driven alert on crossing `low_stock_threshold`, per-store digest to ops, configurable per SKU/store. | claude-code | S | E05-Th01-S01-T03 | not_started
E05 — Inventory & partners | Th01 — Dark-store inventory | S01 — As an ops manager, I want GRN, adjustments and cycle counts with a full audit trail and alerts, so that system stock matches shelf stock | E05-Th01-S01-T05 | Stock event propagation ≤ 60 s | `stock.*` consumers invalidating the Redis catalog cache and updating Meili so a zeroed SKU disappears from browse and search within 60 s. | claude-code | M | E05-Th01-S01-T03, E02-Th03-S01-T02 | not_started
E05 — Inventory & partners | Th02 — Partner onboarding & feed ingestion | S01 — As a partner manager, I want to onboard stores and ingest their stock via API or CSV, so that coverage grows without lying about stock | E05-Th02-S01-T01 | Partner store onboarding + partner users | Partner store creation (type=partner, commission_pct), partner-role user provisioning row-scoped to the store, zone mapping. | claude-code | M | E02-Th01-S01-T01, E01-Th03-S02-T03 | not_started
E05 — Inventory & partners | Th02 — Partner onboarding & feed ingestion | S01 — As a partner manager, I want to onboard stores and ingest their stock via API or CSV, so that coverage grows without lying about stock | E05-Th02-S01-T02 | API feed ingestion + SKU mapping/merge | `partner_feed` entity, authenticated push API, mapping/merge of partner SKUs to master catalog, `last_ingested_at` + row counts. | claude-code | L | E05-Th02-S01-T01, E05-Th01-S01-T01 | not_started
E05 — Inventory & partners | Th02 — Partner onboarding & feed ingestion | S01 — As a partner manager, I want to onboard stores and ingest their stock via API or CSV, so that coverage grows without lying about stock | E05-Th02-S01-T03 | CSV feed ingestion + rejection report | Scheduled/uploaded CSV to object storage, worker ingestion, row-wise validation, rejection report artifact with reasons, no partial-row corruption. | claude-code | M | E05-Th02-S01-T02, E01-Th01-S02-T06 | not_started
E05 — Inventory & partners | Th02 — Partner onboarding & feed ingestion | S01 — As a partner manager, I want to onboard stores and ingest their stock via API or CSV, so that coverage grows without lying about stock | E05-Th02-S01-T04 | Freshness evaluation + BR-6 degraded listing | `freshness_status` computed on a pinned ≥ 15:00 = stale boundary, degraded listing copy, exclusion from fast-ETA promises, fleet-wide staleness metric + alert. | claude-code | M | E05-Th02-S01-T02, E02-Th01-S01-T05 | not_started
E05 — Inventory & partners | Th02 — Partner onboarding & feed ingestion | S01 — As a partner manager, I want to onboard stores and ingest their stock via API or CSV, so that coverage grows without lying about stock | E05-Th02-S01-T05 | Partner order notify, READY & timeout auto-cancel | Partner notification on `order.placed` (dashboard push + SMS fallback), partner READY transition feeding dispatch, confirmation-timeout auto-cancel (release + refund + notify + exception + fill-rate), commission line on order. | claude-code | L | E05-Th02-S01-T01, E03-Th03-S01-T07, E04-Th05-S01-T02 | not_started
E06 — Client apps | Th01 — Customer mobile app (React Native) | S01 — As Priya, I want to order in under two minutes on my phone, so that quick commerce actually feels quick | E06-Th01-S01-T01 | App shell, navigation & shared design system | RN + Hermes app skeleton, navigation graph, shared design-system package with web, theming/dynamic type, cold-start budget instrumentation, OTA update channel. | claude-code | L | E01-Th01-S01-T01 | not_started
E06 — Client apps | Th01 — Customer mobile app (React Native) | S01 — As Priya, I want to order in under two minutes on my phone, so that quick commerce actually feels quick | E06-Th01-S01-T02 | Screen batch — auth & address (SC-001, SC-002, SC-003, SC-004, SC-020) | OTP request/verify screens, session/refresh handling, GPS permission + auto-detect, manual-entry fallback, address book CRUD, not-serviceable + notify-me state. | claude-code | L | E06-Th01-S01-T01, E01-Th03-S01-T03, E02-Th01-S01-T04 | not_started
E06 — Client apps | Th01 — Customer mobile app (React Native) | S01 — As Priya, I want to order in under two minutes on my phone, so that quick commerce actually feels quick | E06-Th01-S01-T03 | Screen batch — browse, search & PDP (SC-005, SC-006, SC-007, SC-008) | Home/category browse with skeleton loads, search with typo-tolerant results + empty-state alternates, product detail, unavailable-at-store state. | claude-code | L | E06-Th01-S01-T02, E02-Th02-S01-T04, E02-Th03-S01-T03 | not_started
E06 — Client apps | Th01 — Customer mobile app (React Native) | S01 — As Priya, I want to order in under two minutes on my phone, so that quick commerce actually feels quick | E06-Th01-S01-T04 | Screen batch — cart, checkout & payment incl. COD (SC-009, SC-010, SC-011, SC-012, SC-013) | Optimistic cart with cap reasons, single-store switch prompt, bill summary + coupon apply/failure reasons, ETA promise display, gateway SDK payment sheet, COD option honouring BR-5 eligibility, failure retry/switch with cart intact. | claude-code | L | E06-Th01-S01-T03, E02-Th04-S01-T03, E02-Th05-S01-T02, E03-Th03-S01-T02, E03-Th04-S01-T01 | not_started
E06 — Client apps | Th01 — Customer mobile app (React Native) | S01 — As Priya, I want to order in under two minutes on my phone, so that quick commerce actually feels quick | E06-Th01-S01-T05 | Screen batch — tracking, history, rating & offline cache (SC-014, SC-015, SC-016, SC-017, SC-018, SC-019) | Live map tracking over WS with polling fallback, substitution prompt (60 s), cancel flow, order history + reorder, rating + reason picker, on-device cart/catalog cache with sync-on-reconnect. | claude-code | L | E06-Th01-S01-T04, E04-Th04-S01-T04, E03-Th01-S02-T03, E04-Th01-S01-T04 | not_started
E06 — Client apps | Th02 — Customer web storefront (Next.js) | S01 — As Sunita, I want the same journey on the web, so that a big basket is comfortable on a bigger screen | E06-Th02-S01-T01 | Next.js shell + ISR catalog pages | App router skeleton on the shared design system, SSR/ISR category + PDP pages served from CDN, image optimization, Core-Web-Vitals budget. | claude-code | L | E06-Th01-S01-T01, E02-Th02-S01-T03 | not_started
E06 — Client apps | Th02 — Customer web storefront (Next.js) | S01 — As Sunita, I want the same journey on the web, so that a big basket is comfortable on a bigger screen | E06-Th02-S01-T02 | Web auth, location & serviceability | OTP login, session/refresh in httpOnly cookies, location detection + manual address, not-serviceable + notify-me, address book. | claude-code | M | E06-Th02-S01-T01, E01-Th03-S01-T03, E02-Th01-S01-T04 | not_started
E06 — Client apps | Th02 — Customer web storefront (Next.js) | S01 — As Sunita, I want the same journey on the web, so that a big basket is comfortable on a bigger screen | E06-Th02-S01-T03 | Web cart, checkout, payment & COD | Cart parity with the app (same server cart), bill/coupon UI, ETA promise, gateway checkout, COD selection per eligibility, XSS-safe rendering of user-supplied fields. | claude-code | L | E06-Th02-S01-T02, E02-Th04-S01-T01, E03-Th03-S01-T02, E03-Th04-S01-T01 | not_started
E06 — Client apps | Th02 — Customer web storefront (Next.js) | S01 — As Sunita, I want the same journey on the web, so that a big basket is comfortable on a bigger screen | E06-Th02-S01-T04 | Web tracking, history & accessibility pass | Tracking map with WS + polling fallback, order history/reorder/invoice download, WCAG 2.1 AA audit + fixes across all web surfaces. | claude-code | M | E06-Th02-S01-T03, E04-Th04-S01-T04, E03-Th01-S02-T02 | not_started
E06 — Client apps | Th02 — Customer web storefront (Next.js) | S01 — As Sunita, I want the same journey on the web, so that a big basket is comfortable on a bigger screen | E06-Th02-S01-T05 | Web substitution prompt & order rating (SC-015, SC-018) | Web parity for the two remaining customer surfaces: blocking substitution modal with the 60 s countdown (accept → line swap + bill delta, reject/timeout → line refund) launched over the open web screen, and the post-delivery rating screen with the ≤ 3-star reason picker; DELIVERED-only rating enforced server-side. | claude-code | M | E06-Th02-S01-T04, E06-Th01-S01-T05, E04-Th01-S01-T04, E03-Th01-S02-T03 | not_started
E06 — Client apps | Th03 — Rider app (React Native, Android) | S01 — As Ravi, I want a minimal app that offers me jobs and gets me paid, so that my shift has no friction | E06-Th03-S01-T01 | Rider app shell, auth, shift toggle & earnings | RN shell in the mobile monorepo, phone-OTP login with device binding, online/offline toggle, day's deliveries + earnings screens. | claude-code | L | E06-Th01-S01-T01, E04-Th03-S01-T03 | not_started
E06 — Client apps | Th03 — Rider app (React Native, Android) | S01 — As Ravi, I want a minimal app that offers me jobs and gets me paid, so that my shift has no friction | E06-Th03-S01-T02 | Job offer screen with 30 s countdown | WS-delivered offer with distance/payout/countdown, accept/decline actions, race-safe UI when the offer expires or is taken. | claude-code | M | E06-Th03-S01-T01, E04-Th02-S01-T02 | not_started
E06 — Client apps | Th03 — Rider app (React Native, Android) | S01 — As Ravi, I want a minimal app that offers me jobs and gets me paid, so that my shift has no friction | E06-Th03-S01-T03 | Pickup/drop flow with proof + COD collect | Navigation deep-link handoff (maps provider [OPEN]), pickup OTP/scan, drop OTP/photo capture + upload, COD collect amount + collection confirmation step. | claude-code | L | E06-Th03-S01-T02, E04-Th03-S01-T02, E03-Th04-S01-T03 | not_started
E06 — Client apps | Th03 — Rider app (React Native, Android) | S01 — As Ravi, I want a minimal app that offers me jobs and gets me paid, so that my shift has no friction | E06-Th03-S01-T04 | GPS beacon with offline buffering | 4 s cadence GPS streaming over WS, batching, offline buffer with drain-on-reconnect, battery/foreground-service handling. | claude-code | M | E06-Th03-S01-T01, E04-Th04-S01-T01 | not_started
E07 — Admin dashboard | Th01 — Admin shell & RBAC surfaces | S01 — As an admin owner, I want a fast, keyboard-friendly console that only shows each role its tools | E07-Th01-S01-T01 | Admin SPA shell + login/TOTP + role-based nav | React + Vite SPA, code-split routes, email/password/TOTP login, session handling, nav rendered from the role's permission set. | claude-code | L | E01-Th03-S02-T01, E06-Th01-S01-T01 | not_started
E07 — Admin dashboard | Th01 — Admin shell & RBAC surfaces | S01 — As an admin owner, I want a fast, keyboard-friendly console that only shows each role its tools | E07-Th01-S01-T02 | RBAC-driven UI surfaces + user/role management | Permission-aware component gating (never the only enforcement), user/role admin screens, partner-scoped views, read-only mode. | claude-code | M | E07-Th01-S01-T01, E01-Th03-S02-T02 | not_started
E07 — Admin dashboard | Th02 — Live ops dashboard & exception queue | S01 — As Neha, I want to run the day by exception, so that I intervene fast without watching everything | E07-Th02-S01-T01 | Live ops board (orders, riders, stores) | WS-subscribed board of active orders, rider positions and store load, ≤ 30 s freshness, filters by zone/store/state. | claude-code | L | E07-Th01-S01-T01, E04-Th04-S01-T02 | not_started
E07 — Admin dashboard | Th02 — Live ops dashboard & exception queue | S01 — As Neha, I want to run the day by exception, so that I intervene fast without watching everything | E07-Th02-S01-T02 | Exception queue + one-click actions | ETA-breach detector feeding the queue ≤ 30 s alongside stuck/failed-payment/low-rated/no-rider/partner-timeout sources; reassign-rider, call-customer, cancel-refund actions with terminal-state guards. | claude-code | L | E07-Th02-S01-T01, E04-Th02-S01-T04, E03-Th03-S01-T07 | not_started
E07 — Admin dashboard | Th03 — Order management | S01 — As an ops agent, I want to find any order and act on it, so that support issues resolve | E07-Th03-S01-T01 | Order search + full actor timeline | Search by order ID or customer phone (HMAC index), order detail with every state transition, actor and payload diff. | claude-code | M | E07-Th01-S01-T01, E03-Th01-S01-T01 | not_started
E07 — Admin dashboard | Th03 — Order management | S01 — As an ops agent, I want to find any order and act on it, so that support issues resolve | E07-Th03-S01-T02 | Order actions + finance refund approval queue | Modify status / cancel / refund with mandatory reason and audit; finance approval queue for refunds > ₹2,000; state-invalid actions refused. | claude-code | M | E07-Th03-S01-T01, E03-Th03-S01-T07, E03-Th01-S02-T01 | not_started
E07 — Admin dashboard | Th04 — Catalog, inventory, partner, zone & coupon consoles | S01 — As ops/catalog/partner staff, I want consoles for every configurable surface, so that a full day runs without engineering | E07-Th04-S01-T01 | Catalog & SKU console + bulk CSV UI | Category/SKU/image CRUD, per-store price/availability grid, bulk CSV upload with row-level reject report, restricted-category block surfaced with a compliance reason. | claude-code | L | E07-Th01-S01-T01, E02-Th02-S01-T02 | not_started
E07 — Admin dashboard | Th04 — Catalog, inventory, partner, zone & coupon consoles | S01 — As ops/catalog/partner staff, I want consoles for every configurable surface, so that a full day runs without engineering | E07-Th04-S01-T02 | Inventory console (GRN, adjust, cycle count, alerts) | GRN entry, adjustments/cycle counts with mandatory reason, audit trail viewer, low-stock alert list with threshold configuration. | claude-code | M | E07-Th01-S01-T01, E05-Th01-S01-T04 | not_started
E07 — Admin dashboard | Th04 — Catalog, inventory, partner, zone & coupon consoles | S01 — As ops/catalog/partner staff, I want consoles for every configurable surface, so that a full day runs without engineering | E07-Th04-S01-T03 | Partner console: onboarding, feed health & settlement | Partner store onboarding, feed mode/credentials, freshness + staleness indicators, rejection-report viewer, fill-rate scorecard and commission/settlement report; partner-role users see only their own store. | claude-code | L | E07-Th01-S01-T02, E05-Th02-S01-T04 | not_started
E07 — Admin dashboard | Th04 — Catalog, inventory, partner, zone & coupon consoles | S01 — As ops/catalog/partner staff, I want consoles for every configurable surface, so that a full day runs without engineering | E07-Th04-S01-T04 | Zone editor, ETA params & coupon console | Polygon draw/edit with validation errors, store-to-zone mapping, ETA parameter tuning, publish action; coupon CRUD (flat/percent, min cart, max discount, validity, usage limits). | claude-code | L | E07-Th01-S01-T01, E02-Th01-S01-T05, E02-Th05-S01-T02 | not_started
E07 — Admin dashboard | Th05 — Analytics, warehouse & digest | S01 — As a stakeholder, I want KPI dashboards that reconcile with the ledger and a daily digest, so that decisions are data-driven | E07-Th05-S01-T01 | Warehouse sink + KPI dashboards + CSV export | **[OPEN: warehouse engine, decided with cloud vendor]** Redpanda → warehouse forwarder, GMV/orders/AOV/SLA hit/fill-rate/rider-utilization/zone-heatmap dashboards, date-range CSV export, ledger reconciliation checks, empty-range zeroing. | claude-code | L | E07-Th01-S01-T01, E01-Th04-S01-T03, E04-Th04-S01-T04 | not_started
E07 — Admin dashboard | Th05 — Analytics, warehouse & digest | S01 — As a stakeholder, I want KPI dashboards that reconcile with the ledger and a daily digest, so that decisions are data-driven | E07-Th05-S01-T02 | Daily digest at 8 am | Scheduled job composing the KPI digest and delivering via email/Slack, with failure alerting and a re-send command. | claude-code | S | E07-Th05-S01-T01, E04-Th05-S01-T01 | not_started
E08 — Hardening & launch | Th01 — Performance & load | S01 — As the eng lead, I want proof the SLOs hold at launch peak and at 10×, so that NFR-1/2/4/7/9 are facts, not hopes | E08-Th01-S01-T01 | Load harness + browse/search/checkout/tracking runs | **[OPEN: k6 vs Gatling vs artillery]** Load scripts and prod-sized staging profile; execute browse, search, checkout-surge and 10k-socket tracking runs; publish p95/p99 + error-rate report. | claude-code | L | E06-Th02-S01-T01, E03-Th01-S01-T03, E04-Th04-S01-T02 | not_started
E08 — Hardening & launch | Th01 — Performance & load | S01 — As the eng lead, I want proof the SLOs hold at launch peak and at 10×, so that NFR-1/2/4/7/9 are facts, not hopes | E08-Th01-S01-T02 | 10× scale-out drill + mobile cold-start/offline validation | Scale replicas/partitions per runbook and re-run TC-PERF-001..003 at 10× volumes; measure RN cold start ×10 and offline grace on the physical device matrix. | human | M | E08-Th01-S01-T01, E06-Th01-S01-T05 | not_started
E08 — Hardening & launch | Th02 — Security, privacy & compliance | S01 — As the compliance owner, I want ASVS L2, PCI SAQ-A and DPDP proven before launch, so that NFR-5/6/10 gate the release honestly | E08-Th02-S01-T01 | ASVS L2 spot checks, PAN sweep & PII crypto verification | Injection/IDOR/XSS payload runs across app, web, admin and CSV imports; PAN/instrument regex sweep across DB dumps, logs, traces, Redis, object storage; column-crypto + HMAC-index + log-redaction verification. | claude-code | L | E06-Th02-S01-T03, E07-Th01-S01-T02, E03-Th03-S01-T03 | not_started
E08 — Hardening & launch | Th02 — Security, privacy & compliance | S01 — As the compliance owner, I want ASVS L2, PCI SAQ-A and DPDP proven before launch, so that NFR-5/6/10 gate the release honestly | E08-Th02-S01-T02 | DPDP consent + deletion workflow, audit matrix & pen-test prep | Versioned consent capture + re-consent on version bump + processing gates; deletion request → in-place anonymization with statutory carve-outs, audit-logged and confirmed to the user; audit completeness matrix executed across every mutation incl. COD collection; scope pack + evidence for the external pen test. | claude-code | L | E08-Th02-S01-T01, E01-Th03-S03-T02, E03-Th04-S01-T03 | not_started
E08 — Hardening & launch | Th03 — Chaos, resilience & data safety | S01 — As the on-call engineer, I want the failure modes rehearsed, so that NFR-3's 99.9% survives contact with reality | E08-Th03-S01-T01 | Kill switches + chaos game day (pod, AZ, broker, gateway) | Feature flags to shed ratings/analytics/partner ingestion and force COD-only mode; scripted game day: core pod kill, AZ drain, realtime pod kill, Redpanda broker loss, Meili outage, Redis failover, gateway + SMS outage — each with a pre-written blast-radius statement and runbook. | claude-code | L | E08-Th01-S01-T01, E03-Th04-S01-T02, E04-Th04-S01-T03 | not_started
E08 — Hardening & launch | Th03 — Chaos, resilience & data safety | S01 — As the on-call engineer, I want the failure modes rehearsed, so that NFR-3's 99.9% survives contact with reality | E08-Th03-S01-T02 | Backup/restore drill + 24 h soak | Weekly staging PITR restore automation, pre-launch region-loss restore via Terraform measured against RTO/RPO; 24 h soak at 1.5× launch load watching memory, consumer lag, outbox bloat, Redis eviction, socket fd exhaustion. | human | M | E08-Th03-S01-T01, E01-Th01-S02-T03 | not_started
E08 — Hardening & launch | Th04 — Seed data & launch readiness | S01 — As the pod owner, I want the launch city seeded and every runbook written, so that go-live is a checklist, not an adventure | E08-Th04-S01-T01 | Seed data & fixtures (Delhi NCR shaped) | Deterministic seed + faker factories for 60 stores / 50k SKUs / 2k riders / zone polygons / coupons / RBAC roles; fixture set under `code/tests/fixtures/` shared by CI, staging and load runs. | claude-code | M | E02-Th01-S01-T01, E05-Th01-S01-T01, E02-Th05-S01-T02 | not_started
E08 — Hardening & launch | Th04 — Seed data & launch readiness | S01 — As the pod owner, I want the launch city seeded and every runbook written, so that go-live is a checklist, not an adventure | E08-Th04-S01-T02 | Launch config, runbooks & go-live checklist | Production ops config (zone polygons, store-zone map, ETA params, BR-5 COD cap, low-stock thresholds, partner cohort), on-call rotation + per-alert runbooks, deploy/rollback runbook, compliance checklist (DLT, gateway onboarding, FSSAI/GST, pen-test sign-off). | human | M | E08-Th04-S01-T01, E08-Th03-S01-T01, E08-Th02-S01-T02, E01-Th02-S01-T04 | not_started